## Template
Task 3_Project Management: Research phase set-up
Issue Type | Summary | Description | Assignee | Functional Role | Sprint | Priority
Story | Working team - Discovery Phase | Ensure resourcing for project by identifying and securing commitment of people from needed departments. | 23456789 | Scrum Master | Sprint 1 | Highest
Sub-task | Identify and appoint resources - replacement from QA team | Identify and assign appropriate resource as QA team fully utilised | 42680754 | QA | Sprint 1 | Highest
Sub-task | Identify and appoint resource - Software Support team | Identify and assign resource from Software Support team | 72855917 | Software support | Sprint 1 | Highest
Story | Prepare business requirements doc | Create business requirement document | 88574839 | Business Analyst | Sprint 1 | High
Sub-task | Check updated BRD format | Obtain updated template for business requirement document and ensure access to all stakeholders | 12894377 | Scrum Master Support Analyst | Sprint 1 | High
Sub-task | Customer focus group | Provide summary of notes from focus group sessions to feed into doc | 82748395 | Marketing | Sprint 1 | High
Story | Competitor research | Conduct review of competitor set to look for gaps in offerings, must have features, etc. | 88574839 | Business Analyst | Backlog | Medium
Story | Create business requirement survey | Complete business requirements survey with key business stakeholders | 43205968 | Product Manager | Sprint 1 | High
Sub-task | Melissa and team's previous business requirement survey | Get survey from Melissa and team from last project for last product to form basis of survey | 43205968 | Product Manager | Sprint 1 | High
Sub-task | Create survey | Create survey using Melissa's old business requirement survey as the basis | 43205968 | Product Manager | Sprint 1 | High
Sub-task | Review survey with Melissa and team | Review new business requirement survey with Melissa and team | 43205968 | Product Manager | Sprint 1 | High
Story | Key stakeholder business requirement survey responses and analysis | Get completion of business requirement survey from key stakeholders | 43205968 | Product Manager | Sprint 1 | High
Sub-task | Send to Marketing team | Completion of survey from marketing | 43205968 | Product Manager | Sprint 1 | High
Sub-task | Send to Product Leadership | Completion of survey from product leadership | 43205968 | Product Manager | Sprint 1 | High
Sub-task | Send to Engineering team | Completion of survey from engineering team | 43205968 | Product Manager | Sprint 1 | High
Sub-task | Review stakeholder responses | Analyse results | 43205968 | Product Manager | Sprint 1 | High
Story | Clarify customer benefits | Convey customer value proposition for solution - e.g., from customer perspective, why are we doing this? What problem does it solve? | 82748395 | Marketing | Backlog | Medium
Story | Prioritise currencies | Rank currencies based on transaction data, to determine which are to be prioritised for launch. | 12894377 | Scrum Master Support Analyst | Backlog | Medium
Sub-task | Get transaction data from product team | Contact data team for data | 12894377 | Scrum Master Support Analyst | Backlog | Medium
Sub-task | Analyse transaction data | Perform analysis | 12894377 | Scrum Master Support Analyst | Backlog | Medium
Sub task | Check for regulatory issues for currencies/countries | Check legal requirements of any proposed launch currencies from dataset | 29485069 | Legal | Backlog | Low
Story | Agree target launch date | Check engineering roadmap and provide rough target date for launch (6 months) | 49985940 | Engineering team | Backlog | Low
Story | Confirm initial budget | Confirm initial budget (may change as business requirements are agreed) | 98760983 | Finance | Sprint 1 | Highest
This Virtual Experience is designed and produced by InsideSherpa Inc (d/b/a Forage, a Delaware incorporation located at 251 Little Falls Drive, Wilmington, Delaware, 19808-1675 United States of America (“Forage”)) for educational purposes only and is subject to the terms and conditions of this website. Nothing presented in this Virtual Experience should be taken as an accurate representation of the HSBC Group’s views or the work undertaken by the HSBC Group. Nothing in this Virtual Experience is intended to promote or advertise any product or service by any member of the HSBC Group of companies. To learn more about HSBC Group’s business visit www.hsbc.com. All tasks, materials, companies and people featured in this Virtual Experience are simulated and entirely fictional. Any resemblance to real persons (either living or dead) or other real-life entities is purely coincidental.

## Staff Directory
Team Member | Function/role | Staff ID
Helen Gordon | Scrum Master | 23456789
Paola Fernandez | Finance | 98760983
Brian Williams | Marketing | 82748395
Melissa Wong | Product Manager | 43205968
Me | Scrum Master Support Analyst | 12894377
Sara Fox | Business Analyst | 88574839
Kurt O'Brien | Legal | 29485069
Jason Lo | Product Manager | 34526334
Sadiq Mohammad | Engineering team | 49985940
Mary Matos | Software support | 72855917
Carlos Cassar | QA | 42680754
This Virtual Experience is designed and produced by InsideSherpa Inc (d/b/a Forage, a Delaware incorporation located at 251 Little Falls Drive, Wilmington, Delaware, 19808-1675 United States of America (“Forage”)) for educational purposes only and is subject to the terms and conditions of this website. Nothing presented in this Virtual Experience should be taken as an accurate representation of the HSBC Group’s views or the work undertaken by the HSBC Group. Nothing in this Virtual Experience is intended to promote or advertise any product or service by any member of the HSBC Group of companies. To learn more about HSBC Group’s business visit www.hsbc.com. All tasks, materials, companies and people featured in this Virtual Experience are simulated and entirely fictional. Any resemblance to real persons (either living or dead) or other real-life entities is purely coincidental.

## Align
S.no | Description | Priority | Spirit | Asignee | Dept | Id
1 | Need to move on this product ASAP | High | 1 | Helen | Scrum Master | 23456789
2 | Hearing large appetite for solution from customers via focus group session | Medium | 1 | Brian | Marketing | 82748395
3 | Think Marketing has notes from session - could use a good summary to feed into business requirements doc | Low | 1 | Brian | Marketing | 82748395
4 | Couple of competitors already active in this space - business analyst (Sara) to conduct review of competitors to look for gaps in offerings, must-haves, etc. | Medium | 1 | Sara | Business Analyst | 88574839
5 | Need something quick here, needs to start now to be ready by middle of W2 | High | 1 | Sara | Business Analyst | 88574839
6 | Need to take four weeks max to get business requirements doc done | High | 1 | Helen | Scrum Master | 23456789
7 | Need to get going quickly otherwise high risk of delay if resources diverted to other projects | High | 1 | Helen | Scrum Master | 23456789
8 | Mary unclear who will be assigned to project from Support team | Medium | 1 | Helen | Scrum Master | 23456789
9 | QA team is already fully utilised - Carlos will have to find bandwidth there | Medium | 1 | Helen | Scrum Master | 23456789
10 | Team needs to be agreed this week | High | 1 | Helen | Scrum Master | 23456789
11 | Business requirement survey needed ASAP | High | 1 | Helen | Scrum Master | 23456789
12 | Should go to key stakeholders across the business | Medium | 1 | Helen | Scrum Master | 23456789
13 | Most likely head of customer experience, marketing team, product leadership, engineering | Low | 1 | Helen | Scrum Master | 23456789
14 | Product managers (Melissa & team) created one for the last product, was well received | Low | 1 | Helen | Scrum Master | 23456789
15 | Use this as a basis and review the new business requirement survey before sending out to stakeholders | Medium | 1 | Helen | Scrum Master | 23456789
16 | Analysis needed on stakeholder responses (W1) | Medium | 1 | Helen | Scrum Master | 23456789
17 | I'm not sure we are clear on the customer benefits? | Low | 1 | Helen | Scrum Master | 23456789
18 | Clear that there are benefits and worth pursuing, but need to be able to start telling the customer valuesuccinctly | Medium | 1 | Helen | Scrum Master | 23456789
19 | Marketing to own this (Brian) | Low | 1 | Brian | Marketing | 82748395
20 | Need to go through transaction data to determine which currencies are priority | Medium | 1 | Helen | Scrum Master | 23456789
21 | You can get transaction data from the product team, but they don't have bandwidth to do the analysis | Low | 1 | Helen | Scrum Master | 23456789
22 | You should be able to analyse | Low | 1 | Helen | Scrum Master | 23456789
23 | Should be a quick exercise once we get the data | Low | 1 | Helen | Scrum Master | 23456789
24 | Sadiq asked if there are obvious regulatory issues that we should be aware of for any of the currencies/countries | Medium | 1 | Sadiq | Engineering team | 49985940
25 | Kurt from Legal will check that over and report back when back from holiday in a few weeks | Low | 1 | Kurt | Legal | 29485069
26 | Business requirement document format has recently been updated and standardised across company | Low | 1 | Helen | Scrum Master | 23456789
27 | Make sure we are using correct format and ensure access for all who need it | Low | 1 | Helen | Scrum Master | 23456789
28 | Would like to launch in 6 months to steal competitor advantage | High | 2 | Sadiq | Engineering team | 49985940
29 | But need to confirm with overall company roadmap on scheduling | Medium | 2 | Sadiq | Engineering team | 49985940
30 | Engineering team (Sadiq) to confirm rough target for launch | Medium | 2 | Sadiq | Engineering team | 49985940
31 | Finance (Paola) to confirm initial budget (which may evolve based on how business requirement shapes up) | Medium | 2 | Paola | Finance | 98760983
32 | Need to get this from her ASAP (W1) | High | 2 | Paola | Finance | 98760983
33 | Absolute priority number 1 is to lockdown working team | High | 1 | Helen | Scrum Master | 23456789
34 | Not yet confirmed who will be dedicated to this from most departments | Medium | 1 | Helen | Scrum Master | 23456789
35 | This is urgent! Helen to confirm | High | 1 | Helen | Scrum Master | 23456789
36 | We are already short on resources from QA | Medium | 1 | Helen | Scrum Master | 23456789

## Sheet3 (hidden)
Story | Highest | Sprint 1
Sub-task | High | Backlog
Medium
Low
Lowest